## Budget Tracker
PROJECT BUDGET TRACKER
Project Name: | [Enter Project Name] |  | Total Approved Budget: | 500000
Category | Item Description | Budgeted Cost | Actual Cost | Variance | % Used | Notes
Labour | Project Team Salaries | 150000 | 142000 | 8000 | 94.67%
Materials | Equipment & Supplies | 80000 | 85000 | -5000 | 106.2% | Slight overrun - see notes
Software | MS Project Licenses | 20000 | 18000 | 2000 | 90%
TOTALS |  | 250000 | 245000 | 5000
Budget Remaining: | 255000

## Risk Register
PROJECT RISK REGISTER
Project Name: | [Enter Project Name]
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Plan | Owner | Status
R01 | Key supplier delivery delay | Procurement | 3 | 4 | 12 | Identify backup suppliers | Project Manager | Open
R02 | Scope creep from client requests | Scope | 4 | 3 | 12 | Formal change control process | Business Analyst | Open
R03 | Team member unavailability | Resource | 2 | 3 | 6 | Cross-train team members | HR/Team Lead | Monitoring